Attendora

10-Week Sprint Plan | Team of 2

Project scope: student registration → teacher session → student check-in → attendance record → reports, built with Flutter, Firebase Auth, Cloud Firestore, Firebase Storage, Riverpod, and flutter_test.

| Developers | Kshitiz Poudel, Biraj Chauhan |
| --- | --- |
| Project | Attendora — Smart Attendance System |
| Duration | 10 weeks |
| Tech Stack | Flutter, Dart, Firebase (Auth, Firestore, Storage), Riverpod, flutter_test |

Guiding principle: every week produces something demonstrable. There's no separate “documentation-only” week and no week spent purely on setup without visible progress — the app grows one working piece at a time.

## Week 1 — Project Setup & Requirement Analysis

Goal: Get the foundation running before writing any real feature code.

- Set up the Flutter project structure (lib/core, lib/features, feature-first architecture)

- Create a Firebase project and connect Auth, Firestore, and Storage

- Configure Riverpod for state management

- Set up GitHub repository with a clear branch strategy (main / dev)

- Finalize requirements: define the four user roles — Student, Teacher, Admin, Super Admin

- Draft the complete attendance workflow and initial database requirements

- Start project documentation (README skeleton, requirements doc)

lib/

        core/

          services/

          utils/

          router.dart

        features/

          auth/

          dashboard/

          ...

End of Week — Demo Point: Flutter app builds and runs on an emulator, Firebase project is connected, GitHub repo is organized, and requirements are finalized in writing.

## Week 2 — Database Design & UI Wireframes

Goal: Design the data model and screen flow before building features on top of them.

- Design Firestore collections for users, classes, sessions, and attendance

- Define role-based fields (e.g. institutionId, role, approval status)

- Sketch wireframes: Login, Signup, Role-based Dashboards, Class List, Session Screen

- Draw the system workflow / use-case diagram for all four roles

- Define the service/repository layer needed to talk to Firestore

users/{uid}

        name, email, role, institutionId, status

      classes/{classId}

        teacherId, name, schedule

      sessions/{sessionId}

        classId, startTime, endTime, status

      attendance/{recordId}

        sessionId, studentId, timestamp, status

End of Week — Demo Point: Firestore schema is finalized on paper, wireframes for every core screen are ready, and the use-case diagram maps out how each role moves through the app.

## Week 3 — Authentication

Goal: Get people into the app with the right role and the right access.

- Implement email/password signup and login via Firebase Auth

- Store role and profile data in Firestore on account creation

- Build role-based routing so each role lands on its own dashboard

- Add protected routes so unauthenticated users can't reach app screens

- Write manual test cases for Student, Teacher, Admin, and Super Admin login

End of Week — Demo Point: Signing up or logging in correctly routes a user to their own dashboard based on role, and unauthenticated access is blocked.

## Week 4 — Class & Session Management

Goal: Let teachers create the classes and sessions that attendance will be tracked against.

- Build the "Create Class" flow for teachers

- Build the "Start Session" flow tied to a class

- Store sessions in Firestore with a status field (active / closed)

- Let students view the classes they're enrolled in

End of Week — Demo Point: A teacher can create a class, start a session, and see it correctly reflected as active in Firestore and in the app UI.

## Week 5 — Attendance Marking

Goal: Build the core loop the whole app exists for: a student checking in to a live session.

- Build the student check-in flow (manual check-in / QR-based check-in)

- Write attendance records tied to session + student, with duplicate check-in prevention

- Build a live view for the teacher showing who has checked in so far

- Handle edge cases: session not yet started, session already closed, already checked in

End of Week — Demo Point: A teacher starts a session, a student checks in from their device, and the teacher's live view updates to reflect the new attendance record.

## Week 6 — Admin & Super Admin Management

Goal: Add the oversight layer that approves accounts and manages the institution.

- Build the Admin dashboard: manage teacher/student accounts, approve pending signups

- Build the Super Admin dashboard: oversee all admin accounts across institutions

- Write Firestore security rules enforcing role-based access at the database level

- Test that each role can only access what it's supposed to

End of Week — Demo Point: A newly registered teacher or student account shows as pending, and the Admin can approve or reject it; Super Admin can view activity across all admins.

## Week 7 — Reports & Analytics

Goal: Turn raw attendance records into something a teacher can actually act on.

- Calculate attendance percentage per student and per class

- Build the Teacher Reports screen with history and trends

- Add filtering by date range and class

End of Week — Demo Point: A teacher opens the Reports screen and sees an accurate attendance percentage and history for a real class with real check-in data.

## Week 8 — UI Polish & Branding

Goal: Make the app feel finished, not just functional.

- Apply consistent theming across all four dashboards

- Finalize app branding — icon, splash screen, About page

- Improve loading states, empty states, and error messages throughout

- Add basic in-app alerts for low attendance as an extra, non-MVP feature

End of Week — Demo Point: Navigating through all four roles feels visually consistent, with no placeholder screens or unstyled error states left.

## Week 9 — Testing & Bug Fixes

Goal: Actually test the system end-to-end, not just write code and hope.

- Write unit tests for core logic: auth, attendance marking, report calculation

- Manually QA all four roles end-to-end on a real device/emulator

- Re-verify Firestore security rules (including the Super Admin access rule) against the live project

- Log and fix every bug found this week before moving on

End of Week — Demo Point: flutter test passes for core logic, and a full manual run-through of all four roles shows no blocking bugs.

## Week 10 — Finalization, Demo & Documentation

Goal: Package everything so it's ready to present and hand in.

- Final round of bug fixes and performance polish

- Finalize README with setup and run instructions

- Prepare a demo script and seed sample data/test accounts for each role

- Write the final project report and prepare the presentation

End of Week — Demo Point: A complete, rehearsed walkthrough: Student registers → Teacher starts a session → Student checks in → Teacher views the report — ready to present.

# The 10-Week Roadmap

| Week | Main Goal | Key Deliverable (Demo Point) |
| --- | --- | --- |
| 1 | Setup & Requirements | Flutter + Firebase connected, requirements finalized |
| 2 | Database Design & Wireframes | Firestore schema + wireframes complete |
| 3 | Authentication | Role-based login working end-to-end |
| 4 | Class & Session Management | Teacher creates class & starts a session |
| 5 | Attendance Marking | Student checks in → teacher sees it live |
| 6 | Admin & Super Admin | Approval workflow + oversight dashboard working |
| 7 | Reports & Analytics | Accurate attendance reports per class/student |
| 8 | UI Polish & Branding | Consistent, finished-feeling UI across all roles |
| 9 | Testing & Bug Fixes | Tests passing, no blocking bugs across all roles |
| 10 | Finalization & Demo | Rehearsed full demo + final report ready |

# How the Project Grows Every Week

Rather than building the frontend and backend in isolation for weeks and connecting them at the very end, each week adds one working piece on top of the last:

Week 1: Foundation  ->  Week 2: Design  ->  Week 3: Authentication

      Week 4: Class & Session  ->  Week 5: Attendance Marking

      Week 6: Admin Oversight  ->  Week 7: Reports & Analytics

      Week 8: UI Polish  ->  Week 9: Testing & Fixes  ->  Week 10: Final Product

# MVP vs. Extra Features

Build these first — this is the minimum viable version of Attendora:

- Student / Teacher registration

- Admin approval of new accounts

- Class & session creation

- Student check-in / attendance marking

- Basic attendance reports

Only after the MVP works, layer in extras:

- Certification / profile photo upload

- Low-attendance alerts / notifications

- Advanced analytics (trends, charts)

- QR-based check-in (if not already part of MVP)

Don't start with push notifications, analytics dashboards, or multi-institution features — those come after the core loop works: a teacher starts a session, a student checks in, and the attendance record shows up correctly. Once that works end-to-end, everything else is an enhancement.